## Sheet1
Comments | Key Deliverables | Person Responsible | Activity | 2023-02-27 | 2023-02-28 | 2023-03-01 | 2023-03-02 | 2023-03-03 | 2023-03-04 | 2023-03-05 | 2023-03-06 | 2023-03-07 | 2023-03-08 | 2023-03-09 | 2023-03-10 | 2023-03-11 | 2023-03-12 | 2023-03-13 | 2023-03-14 | 2023-03-15 | 2023-03-16 | 2023-03-17 | 2023-03-18 | 2023-03-19 | 2023-03-20 | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-24 | 2023-03-25 | 2023-03-26 | 2023-03-27 | 2023-03-28 | 2023-03-29 | 2023-03-30 | 2023-03-31 | 2023-04-01 | 2023-04-02 | 2023-04-03 | 2023-04-04 | 2023-04-05 | 2023-04-06 | 2023-04-07 | 2023-04-08 | 2023-04-09 | 2023-04-10 | 2023-04-11 | 2023-04-12 | 2023-04-13 | 2023-04-14 | 2023-04-15 | 2023-04-16 | 2023-04-17 | 2023-04-18 | 2023-04-19 | 2023-04-20 | 2023-04-21 | 2023-04-22 | 2023-04-23 | 2023-04-24 | 2023-04-25 | 2023-04-26 | 2023-04-27 | 2023-04-28 | 2023-04-29 | 2023-04-30 | 2023-05-01 | 2023-05-02 | 2023-05-03 | 2023-05-04 | 2023-05-05 | 2023-05-06 | 2023-05-07 | 2023-05-08 | 2023-05-09 | 2023-05-10 | 2023-05-11 | 2023-05-12 | 2023-05-13 | 2023-05-14 | 2023-05-15 | 2023-05-16 | 2023-05-17 | 2023-05-18 | 2023-05-19 | 2023-05-20 | 2023-05-21 | 2023-05-22 | 2023-05-23 | 2023-05-24 | 2023-05-25 | 2023-05-26 | 2023-05-27 | 2023-05-28 | 2023-05-29 | 2023-05-30 | 2023-05-31 | 2023-06-01 | 2023-06-02 | 2023-06-03 | 2023-06-04 | 2023-06-05 | 2023-06-06 | 2023-06-07 | 2023-06-08 | 2023-06-09 | 2023-06-10 | 2023-06-11 | 2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-15 | 2023-06-16 | 2023-06-17 | 2023-06-18 | 2023-06-19 | 2023-06-20 | 2023-06-21 | 2023-06-22 | 2023-06-23 | 2023-06-24 | 2023-06-25 | 2023-06-26 | 2023-06-27 | 2023-06-28 | 2023-06-29 | 2023-06-30 | 2023-07-01 | 2023-07-02 | 2023-07-03 | 2023-07-04 | 2023-07-05 | 2023-07-06 | 2023-07-07 | 2023-07-08 | 2023-07-09 | 2023-07-10 | 2023-07-11 | 2023-07-12 | 2023-07-13 | 2023-07-14 | 2023-07-15 | 2023-07-16
|  |  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20
|  |  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
| Planning | Planning | [6 empty] | NON WORKING DAYS NON WORKING DAYS | NON WORKING DAYS NON WORKING DAYS | [5 empty] | NON WORKING DAYS NON WORKING DAYS | NON WORKING DAYS NON WORKING DAYS | [5 empty] | NON WORKING DAYS NON WORKING DAYS | NON WORKING DAYS NON WORKING DAYS | [5 empty] | NON WORKING DAYS NON WORKING DAYS | NON WORKING DAYS NON WORKING DAYS | [5 empty] | NON WORKING DAYS NON WORKING DAYS | NON WORKING DAYS NON WORKING DAYS | [5 empty] | NON WORKING DAYS NON WORKING DAYS | NON WORKING DAYS NON WORKING DAYS | [5 empty] | NON WORKING DAYS NON WORKING DAYS | NON WORKING DAYS NON WORKING DAYS | [5 empty] | NON WORKING DAYS NON WORKING DAYS | NON WORKING DAYS NON WORKING DAYS | [5 empty] | NON WORKING DAYS NON WORKING DAYS | NON WORKING DAYS NON WORKING DAYS | [5 empty] | NON WORKING DAYS NON WORKING DAYS | NON WORKING DAYS NON WORKING DAYS | [5 empty] | NON WORKING DAYS NON WORKING DAYS | NON WORKING DAYS NON WORKING DAYS | [5 empty] | NON WORKING DAYS NON WORKING DAYS | NON WORKING DAYS NON WORKING DAYS | [5 empty] | NON WORKING DAYS NON WORKING DAYS | NON WORKING DAYS NON WORKING DAYS | [5 empty] | NON WORKING DAYS NON WORKING DAYS | NON WORKING DAYS NON WORKING DAYS | [5 empty] | NON WORKING DAYS NON WORKING DAYS | NON WORKING DAYS NON WORKING DAYS | [5 empty] | NON WORKING DAYS NON WORKING DAYS | NON WORKING DAYS NON WORKING DAYS | [5 empty] | NON WORKING DAYS NON WORKING DAYS | NON WORKING DAYS NON WORKING DAYS | [5 empty] | NON WORKING DAYS NON WORKING DAYS | NON WORKING DAYS NON WORKING DAYS | [5 empty] | NON WORKING DAYS NON WORKING DAYS | NON WORKING DAYS NON WORKING DAYS | [5 empty] | NON WORKING DAYS NON WORKING DAYS | NON WORKING DAYS NON WORKING DAYS
Demolution Permits
Section 29 application for report and consent
Demolition Plan
Safety Plan
Council submision Planning
Working drawings
Engineering Drawings
Soil Report
Energy eficiency Report
Council Requiremets
footpath report
Insurances
Certificate of title
Waterboard PIC
Form 1 Application
Building Permit
| Demolition / Construction Phase | Demolition & construction phase
temp fence / Amenities
Disconnect the services
Demolition Of Site
Removal of waste
| Base Stage / Base Stage Completion |  | Site Scrape
set out
check set out
site & OHS signs
concerter confirmation
window confirmation
roof tile confirmation
Rammed earth material comfirmation
spoil removal
cross over protection
Safety audit
bin hire
Ramed earth material delivery
rear t/cotta tile delivery
concrete piles
underground communications
underground power
water meter tapping
sewer drains
storm water/AG drains
Commencement of slab
Safety audit
concrete labour
termite part A
slab approval
claim base stage
| Frame Stage / Frame Stage Completion |  | OHS audit
GND Fl scafold order
GND Fl scafold install
Rammed earth construction GND level
window and entry frames order
Safety audit
Internal frame delivery
GND & 1ST Fl Internal frame Install
Subfloor delivery
Truss Roof delivery
supervisor frame QA
1st Fl Scaffold Install
Rammed earth material delivery
First floor Rammed earth formwork
Construction 1st Fl Rammd earth walls
Truss roof install
Safety audit
Supervisor frame inspection
Surveyor frame inspection
frame approval
claim frame stage
| Fixing Stage / Fixing Stage Completion |  | empty bin
2 Roof guard rails install
kitchen & vanity measure
facia and gutters
Window delivery
Safety audit
1st Fl Plumbing rough in
concrete roof tiles install
1st Fl Electrical rough in
solar panel install
Internal Lockup materials doors order
stair measure
Heating Cooling unit install
Subfloor and 1st Fl Ceiling Plaster order
Safety audit
Insulation order
Insulation Delivery
Window Installation
exr lock up material
ext lock up carpenter
Internal wall/subfloor/1st Fl Wall/ Ceiling insualtion
Plaster delivery
Safety audit
Plaster install
ext painter
Install Bath
garage door measure
Water Proof wet areas
Internal door/architraves install
claim lock up
Safety audit
down pipes
down pipe hook up
stair install
kitchen & vanity install
fixing material
fix wet areas carpenter
laundry tub delivery
Safety audit
claim fix stage
| Final Stage / Final Stage Completion |  | painter
plumbing fit off
Garage door delivery
garage door install
ceramic tile delivery
shower & mirror/robe measure
final fit carpenter
light fitting delivery
electrical fit off
shower & mirror/robe install
house clean
int/ext caulking
timber flooring
carpets
fly screens
plumbing appliance delivery
electrical appliance delivery
plumbing install
electrical install
Site Clean
Landscaping
Termite Part B
| Handover |  | client settlement